## web dev practice
58 | 59 | 46 | 50 | 3 | 70
74 | 68 | 38 | 2 | 84 | 16
79 | 87 | 16 | 40 | 79 | 36
47 | 40 | 56 | 15 | 10 | 66
11 | 1 | 13 | 34 | 71 | 93
13 | 5 | 95 | 25 | 32 | 70
87 | 60 | 43 | 85 | 58 | 86
99 | 80 | 69 | 9 | 25 | 20
81 | 78 | 74 | 17 | 11 | 81
4 | 60 | 31 | 65 | 8 | 85
11 | 79 | 17 | 20 | 2 | 10
34 | 7 | 24 | 47 | 61 | 91
85 | 33 | 47 | 27 | 55 | 88
52 | 92 | 64 | 74 | 91 | 74
43 | 18 | 77 | 69 | 18 | 62
72 | 35 | 67 | 80 | 48 | 27
16 | 37 | 85 | 40 | 18 | 38
68 | 58 | 69 | 47 | 16 | 37
80 | 6 | 12 | 82 | 80 | 76
96 | 7 | 82 | 93 | 31 | 71

## Sheet1
Decision | Kick Off | Decision required: AWS vs Confluent Cloud vs Self Hosted Apache Kafka Final Decision - AWS SNS/SQS will be used to sync data from CT to EDAP through MuleSoft | For data sync subscriptions, the choice is between Confluent Cloud and self-hosted Kafka. The Honda SD team prefers self-hosted Kafka due to the separate license requirement, but the Commercetools team does not support Kafka. Deloitte is currently collaborating with CT to explore the feasibility of using Kafka with CT. If this is not possible, Honda may need to acquire Confluent Cloud. The final decision is still pending. On 7/10, Jaldeep confirmed that the team have decided to go with AWS and not Confluent Cloud or Apache Kafka. Hence logging the decision. | Whey Joo Jaldeep | 6/21 7/5 7/11 | Closed | [6/17] Pending data sync design decisions, dependent on decision of AWS vs. ConfluentCloud (#32) [6/20] Nabeel has scheduled a meeting with Honda architects on 6/21 to get the final decision on ConfluentCloud vs AWS. [6/21] Team decided to proceed with ConfluentCloud for Data sync during today's decision call (6/21). Hence AWS will not be considered for outbound events. [6/25] During tech stack discussion, Gaurav discussed the probability to use Self hosted Kafka instead of Confluent Cloud. Decision is still pending [7/4] Follow up discussion scheduled on 7/5 to get the final decision from SD Team [7/10] Jaldeep confirmed to proceed with AWS and not with
Decision | Email: DET Screen (Incentives) Summary | Additional custom screens for additional financial types is out of scope for R1 | During workshops, there has been a request to build additional finance type custom screens in CT apart from the agreed scope of MVP1. However, on 7/7, Whey Joo confirmed that the scope of finance type will be as per original scope of MVP1 - Lease, finance, cash and residuals only. The additional finance type screens willl be built in future releases MVP3. Confirmation for the following questions: 1. Listed Financial Types are not Being Used in DET: 1. NonStackable Rebates- Finance NSTD 2. Lease - Government Incentives 3. Finance - Government Incentives 4. Cash - Government Incentives 5. Sales Promotion 6. NonStackable Rebates- Lease NSTD 7. NonStackable Rebates- NonStackable Trading Dollar (NSTD) 8. Stackable Rebates- Trading Dollars 9. Stackable Rebates- APS Loyalty Dollars 10. Stackable Rebates- Cash or Maintainence Package 11. Stackable Rebates- CRM Dollars 2. National Level mapping at Factory Option (Transmission) level is not applicable for Autos, Is this the case with Non-Autos as well? 3. ProgramCode is not being entered through DET for any financial Type. 4. Financed Range: 0-80000, Is fixed for Auto productLine.? Under “Retail Finance”, we have a checkbox ‘PPSA not Eligible’, which is not being used anywhere. | Nabeel Moloo Lan Nguyen Lance Goosen | 6/13 6/14 6/18 6/28 7/3 | Closed | [6/14] Updated the due date as the action item is open. [6/17] Victor to review email [6/20] Nabeel to send the response from Victor by 6/20 [6/27] @Dilip Chordia, Minal Please provide update [7/3] These financial types are delta to CT Data Model and havent been discussed in discovery as well as in technical workshops. As discussed with Priyanka on 06/28, this will be further discussed with Whey Joo on next steps. [7/4] Priyanka have sent a note to WJ to confirm if this needs to be added in scope. Awaiting response. [7/7] As per Whey Joo's confirmation on (7/7), Custom screens will be developed in Salesforce and Honda will take care of it. Custom screens for additional financial types are also parked for now, it will be revisited during MVP3 (in Salesforce).
Decision |  | Workflow requirement for Custom screens in CT | The workflow requirements for CT data updates/authoring were finalized on 6/28 by Whey Joo. The details are captured below. Hence the decision is closed. Workflow process for content approval i.e. 1. Content creator creates content 2. CT triggers notification to content approver 3. Any subsequent update from content creator will trigger notification content approver 4. Content approver approves content 5. CT moves content to production In Scope: 1. Email to approver (in-scope) 2. Rejection email notification (in-scope) Out of scope: 1. Record Locking (Out of scope as not recommended in CT) 2. Minor Version (Out of scope as not recommended in CT) 3. Avoid Multiple Notification (Out of scope as not recommended in CT) | Deloitte Team | 6/21 6/28 | Closed | [7/2] Whey Joo confirmed on 6/28 to go with simple workflow process for content approval i.e. 1. Content creator creates content 2. CT triggers notification to content approver 3. Any subsequent update from content creator will trigger notification content approver 4. Content approver approves content 5. CT moves content to production In Scope: 1. Email to approver (in-scope) 2. Rejection email notification (in-scope) Out of scope: 1. Record Locking (Out of scope as not recommended in CT) 2. Minor Version (Out of scope as not recommended in CT) 3. Avoid Multiple Notification (Out of scope as not recommended in CT) @Bala and @Matt aligned to this and the document to include the APIs have been created accordingly.
Decision |  | Warranty will be applied at National Level for MVP1 | As per existing system, Warranty is applied at global level, however, during workshops, Victor confirmed on 6/25 to incorporate additional change in Product Data Model to apply Warranty at province level. On 7/7, Whey Joo confirmed that Warranty changes to have it at province level will be considered in MVP3 and not MVP1. | Victor Chard | 6/19 6/26 7/3 7/5 | Closed | [6/20] New functional requirement – Warranty packages will be based on Provinces. Warranty packages will be authored in CT. It has to be synced to EDAP via MuleSoft. Business needs to confirm this requirement to proceed further. Nabeel will discuss with business and get back. ETA - 26 [6/26] - Victor provied the requirements. Minal to confirm if these are incorporated in the data model [6/27] @Dilip Chordia, Minal Please provide update [7/2] Victor confirmed on 6/25 that Warranty will be an additional attribute in CT. @Minal please confirm if you have accomodated this in CT data model. Refer Priyanka's email on 7/2. [7/3] These new attributes on Warranty and Specifications are delta to CT Data Model and havent been discussed in discovery as well as in technical workshops. As discussed with Priyanka on 06/28, this will be further discussed with Whey Joo on next steps. [7/4] Priyanka have sent a note to WJ to confirm if this needs to be added in scope. Awaiting response. [7/7] As per Whey Joo's confirmation on (7/7), Warranty changes to have it a province level will be addressed in MVP3
Decision | Data Sync Workshop Notes | CT to EDAP data sync will be real-time | Honda SD Team and Deloitte team collaboratively alligned on 6/11 to go with event driven real-time approach for data sync between CT and EDAP. |  |  | Closed | Yes, everyone present on the 6/11 call aligned on the event driven real-time approach. If we find a serious limitation down the road and we may need to revisit.
Decision | Data Sync Workshop Notes | Data flow decision between environments | The environments will only be synced downwards for the data sync process - Typically do not do cross environment data connection | Henish Nabeel Matt | 6/14 | Closed | Everyone present on the 6/14 call aligned that data should not be synced upwards
Decision |  | Data Sync requirements and alignment between Honda & Deloitte SD team | Following decisions were made during the Data sync workshop on 6/19: 1. Mulesoft will send data to commercetools only after successfully sending data to EDAP. 2. The requirements and solution design for: the business process for managing data in MDA, the data entities stored in MDA, how that data is sent to MuleSoft, and how MuleSoft orchestrates sending the data to EDAP and CT, is out of scope of the commercetools project, and will be handled in the T1/T3 project. 3. Scope of the MDA to CT data sync solution design for the commercetools project will only include the interface design, which includes: a. Identifying the commercetools APIs that Mulesoft will need to call b. Providing the API Payloads c. Based on the data mapping, which MDA attributes are mapped to which API attributes 4. commercetools project does not need to be concerned with Start Date, End Date, Internal Scheduled Publish Date, External Scheduled Publish Date, it is complex logic that will be handled in MDA and EDAP. 5. commercetools will only consume data sent by Mulesoft. a. There was some discussion if the data to populate the ct data model would come from PRISM, DataStage, EDAP, in addition to MDA, that would scope would be apart of the T1/T3 project, and Mulesoft would be responsible for consolidating the data and sending it to commercetools. | Henish Nabeel Matt | 6/14 | Closed | Everyone present on the 6/19 call aligned on the mentioned items
Decision |  | CT APIs to be used to support T1/T3 application | During discovery, the decision made was CT Model and Finance APIs will be used to import T1/T3 application. However, during workshop we heard that EDAP API will be used to support T1/T3 application. Received confirmation from Whey Joo on 6/27, that CT model & Finance APIs will be used for T1/T3 imports. This is aligned as per discovery decision. | Beavis Nabeel Whey Joo | 6/24 | Closed | [6/26] Yet to get a confirmation [6/27] Whey Joo confirmed on [6/27] that CT model and Finance APIs will be used for T1/T3 imports.
Decision | Product Data Model | Match naming convention of CT product model with EDAP | During design workshops (6 weeks), team worked on Product model and data mapping with EDAP, however the naming convention was unique to CT. On 7/6, Whey Joo confirmed that CT Product Model naming convention should match to EDAP. | Whey Joo | 7/7 | Closed | [7/6] As confirmed by Whey Joo on 7/6, we need to match the naming convention of data model with EDAP in Release 1.
Decision | Model APIs User Stories Workshop | 9 Model APIs - Required to be developed in CT or not? | Honda team (Lan) approved Model API user stories (14 out of 23) for Accessories, Specs, Warranty, Offers, and Loyalty. Lan mentioned the remaining 9 stories require steerco review as the New BAP (MDA design) implementation project is running in parallel, and these Model APIs may not be needed based on the current design and development progress. | Lan Nabeel | 7/16 | Closed | [7/11] Lan will discuss with steerco and provide us a decision [08/01] Lan confirmed that - The remaining 9 stories has already been approved. Steerco has confirmed to proceed with the remaining Model API stories.
Decision | Project Level | CT project timeline extended by 6 weeks | To match the MuleSoft implementation timeline (24th July to 9th Oct), overall CT project timeline have been extended by 6 additional weeks. The new go-live date will be 19th Nov. The decision was confirmed by Jaldeep on 7/10. | Jaldeep | 7/10 | Closed
Decision | Project Level | Deloitte to submit CR for extension of 6 weeks | As per RAID# 118, the overall project timeline have been extended by 6 weeks. Deloitte to create a Change Request to accommodate the extension and send over to Honda team for review | Shahzad Priyanka | 7/15 | Closed | [08/22] CR was signed by Honda on August 21st.
Decision | Project Level | Business and Technical Decisions ultimate owners are Jaldeep and Whey Joo | All decisions on scope change, project timeline, solution approach, design needs to be validated / confirmed by Jaldeep and Whey Joo | Shahzad | 7/11 | Closed
Decision | Custom Screens | BE Services for Custom Screens in SF will be implemented in Mulesoft | All the custom screens will be created in Salesforce as decided on 7/6. Honda SD Team, Deloitte and MuleSoft team decided that the backend services to support Custom screens will be implemented in MS. The product data will be supplied by CT. | Henish Parag Nabeel | 7/11 | Closed
Decision | Model APIs User Stories Workshop | Model API Stories Approval | Model API User stories have received approval from Lan & Honda Team | Lan | 7/12 | Closed
Decision | Custom Screens | Custom screens will be built in Salesforce | On 7/6, Whey Joo confirmed that Honda have decided to build custom screens for financial types in Salesforce and not in CT. RAID# 22 will be descoped as per this decision. | Whey Joo | 7/6 | Closed
Decision | Additional Specs | Additional details to be incorporated in data model for specs | For the existing sheet for specifications: - New fields called specCategory for both English and French languages have been added. In the data model: - Two new worksheets, Loyalty Offers and Incentive Offers, have been created based on confirmation from Lan. These additions are necessary for the Model APIs. For all worksheets: - New attributes have been added, including: - EXTRNL_PUBLISH_DT - EXTRNL_PUBLISH_END_DT - BUS_KEY_DEL_IND | Whey Joo | 7/6 | Closed | [7/6] As per Whey Joo's confirmation, we need to incorporate these additional specs in CT product Data Model for MVP1
Decision | Product Data Model | Accessory Base Product attributes not to be mapped by EDAP | Check and confirm if accessory base product attributes are needed for DET/EDAP or if it should remain only for commercetools perspective | Pratik | 7/10 | Closed | Accessory base product attributes will be used only for CT. EDAP system need not map these attributes. EDAP will only map the Accessory variant attributes
Decision | Product Data Model | Warranty packages to follow DET and not EDAP | Confirm if warranty packages need to be maintained at a model or transmission level On 7/11, Honda team decided: Warranty packages will be maintained at transmission level as per the current design based on DET | Victor Chard | 7/10 | Closed | Warranty packages will be maintained at transmission level as per the current design based on DET
Decision | Authentication | Okta to be used by MuleSoft and CT for API authentication | Honda SD team decided to go with oAuth 2.0 (Okta) to authenticate any APIs between CT and MuleSoft | Henish Parag Matt Nabeel | 7/11 | Closed
Decision | User Stories Workshop | Province Code in Model APIs | Confirm if province code is required at trim/transmission leve as there is a reference under Model APIs | Lan Nguyen | 7/15 | Closed | Lan confirmed that province code will not be related to trim/ transmission. Province code based details will be used for calculations purposes by mulesoft Ct to return data not based on province code for trim/ transmission
Decision | User Stories Workshop | "To be Removed" in Model APIs | we have found some fields which were marked as ‘to be removed’ but are present in the Model API responses. Please confirm if this is required for future state Model APIs. | Lan Nguyen | 7/15 | Closed | Lan confirmed that if any attribute is found in model api documentation that was discussed as ‘to be removed’ during the data model workshops, such attributes will be considered as 'not required ' in model api as well
Decision | Custom Screens | Salesforce Custom Screens will sync directly to EDAP | Salesforce Custom Screens will sync the data to EDAP directly, there is no need to sync from CT to EDAP as well |  | 7/16 | Closed
Decision | Workflows Workshop | Start & End Date Time Field Iclusion in Model | Nabeel and Shahzad aligned on implementing a new T1 go-live start date / time and T1 go-live end date / time. This will be used as a flag to montior when content will go to T3 site | Shahzad Nabeel Lan Nguyen |  | Closed
Decision | AWS | Honda will be responsible for any AWS development | On 7/23, Sarah confirmed that Honda team will be responsible for any AWS development work. Commercetools team will continue providing support as and when required. | Sarah | 07/23 | Closed
Decision | DPoP | Is DPoP required to be implemented for CT APIs? Final Decision: Since CT does not support enabling DPoP , we will not be using it for the API calls. | Initially the plan was to use CT auth to authenticate and call CT APIs, but the SD team wanted to use their own Identity Provider (IDP) which is Okta. We ran a successful POC around Okta to use Okta credentials to obtain an access token that will be used to call CT APIs. Gaurav now wants to explore further Demonstrating Proof-of-Possession (DPoP) which will help prevent unauthorized parties from using leaked or stolen access tokens. | Parag Gaurav Nabeel | 8/2 | Closed | [7/23] Honda SD team need to assess the impact of not having DPoP and decide if this is something really required in this release or can be added later, by July 30th [7/25] Gaurav, Shahzad, and team made the final decision during Okta session that since CT does not support enabling DPoP , we will not be using it for the API calls.
Decision | Custom Screens | Inactive / Active flag requirement | Eoghan and Parag needs to align if the active/inactive flag is needed or not. | Eoghan McMullen | 7/25 | Closed | [08/22] Custom Screens are not needed anymore.
Decision | Data Model Publish date | Final decision on use of T1T3 Publish Date fields Final Decision provided by Pratik: "Web Publish Date" and "Web Publish End Date" fields will only be on Trim, Transmission and Sub Model | Provide final decision on the use of “t1t3 external publish date” and "t1t3 external publish end date” fields "t1t3 external publish date" and "t1t3 external publish end date" have been renamed to "Web Publish Date" and "Web Publish End Date" "Web Publish Timestamp" and "Web Publish End Timestamp" fields will only be on Trim, Transmission and Sub Model | Eoghan McMullen | 7/31 | Closed | [08/20] Final decision provided.
Decision | Custom Screens | Final decision: Custom Screens data will come from MDA not CT. With this entire EPIC PCD-23 Merchant Centre Custom Views (FE & BE) is out of scope for MVP1&2 | Salesforce Custom Screens will receive data from MDA. Once the data is approved and synced in EDAP, MuleSoft will push the data to CT which will be part of data sync process. This was confirmed by Eoghan on July 25th via Email. RAID# 121 is invalid based on this decision | Eoghan McMullen | 7/25 | Closed
Decision | Architecture Review | CT Connect Limitations - Monitoring & Caching not possible with CT Final Decision - Mulesoft will handle orchestration for processing CT Subscription messages via AWS SNS. It will email approvers and authors, and sync data from CT to EDAP. This involves processing the message, calling CT OOTB APIs, determining the action, and retrieving necessary data. | During architecture review, SD team mentioned as CT connect don’t support API call's monitoring & caching functionality, which would make it non-compliant with Honda IT infrastructure team requirements. Since only one service would be impacted, Gaurav, Matt, and Shahzad are collectively inclined to choose the MuleSoft route instead of using CT Connect. Decision on 8/12: Mulesoft will perform the orchestration required to process CT Subscription messages received via AWS SNS in order to email approvers, email authors, and sync data from CT to EDAP. This orchestration will include processing the message, calling CT OOTB APIs, determining the action to take, and retrieving the data required to perform that action. | Matt Gaurav Shahzad Parag | 08/07 08/12 | Closed | [8/12] Gaurav and SD Team decisded to go with MuleSoft,hence CT connect is out of scope.
Decision | Architecture Review | Subscription mechanism | Gaurav, Shahzad, and Bala aligned we will not be utilizing custom APIs -- only a custom service to manage the data comparison | Gaurav Shahzad |  | Closed
Decision | Okta Demo | MuleSoft to add additional security layer if product data needs to be restricted from certain consumers in future | After the call Albab connected with CT. Currently this level of control is not supported. We understand that in the future, we may need to restrict the information to NOT be share it with certain consumer applications. If this is required in the future, then Mulesoft may have to add another layer of security to account of that. Currently, we do not have a requirement to restrict visibility beyond View and Manage. Currently, View and Manage are available as they fall under Products. | Albab Saifi Shahzad Tariq Gaurav Toshniwal | 08/06 | Closed
Decision | Lite Financial Calculator Workshop (08/08) |  | As per current analysis, Lite finance calculator rules across all Finance Types, however in MVP-1 only 4 Finance types (Retail Lease, Retail Finance, Cash and Residuals) are in-scope for CT [Decision logged in RAID #22] Honda business to confirm if we need to retract the above decision and include all finance types for MVP 1. This decision will impact CT Data model and custom screens in Salesforce respectively. | Nabeel Lan | 08/12 | In-progress
Decision | Lite Financial Calculator Workshop (08/07) | Province Tax and Province Sub Tax | Team aligned that any custom fields (external publish dates, delete indicators) within Province Tax and Province Sub Tax will not be able to be stored as Custom Fields due to CT limitations(CT doesn't allow to create custom fields under Tax categories entities) | Lan Nguyen Victor Pratik | 08/07 | Closed
Decision | Lite Financial Calculator Workshop (08/13) |  | When there are multiple records for a given parameter (ex: Model Code), CT will be able to return only the active record. A record will be considered active if it is in ‘Published’ state and its date range falls in the current date. **This is applicable only if the records don't have overlapping dates |  |  | In-progress
Decision | Offline conversation with Whey Joo | Final Decision on Tax Object: Provincal tax will not be included in the data sync process. | Due to the limitations of the CT OOTB Tax Category, it is not possible to add custom fields such as External or Web Publish Dates to the Provincial Taxes records. As a result, the decision from WJ is to exclude province taxes from the data sync process and instead treat them as data entry fields within CT. | Whey Joo Priyanka | 08/15 | Closed
Decision | Offline conversation with Whey Joo | Final Decision on Luxury Tax: Luxury tax will not be used by Mulesoft in Lite Finance Calculator | Honda business decided that they will host a disclaimer in Inventory UI (T3) that luxury tax is not applied, hence luxury tax will not be used by MuleSoft for any calculation in Lite Finance Calculator. | Whey Joo Priyanka Nabeel | 08/15 | Closed
Decision | Sprint 6 Demo | Update Region-Province Mapping | Region name attribute should be added to Region-Province mapping | Pratik | 2024-09-04 | Closed
Decision | Sprint 6 Demo | Update Retail Lease and Retail Finance Entities | Region attribute to be updated to Region Code in Retail Lease and Retail Finance entities | Pratik | 2024-09-04 | Closed
Decision |  | Add new Attributes to Federal Luxury Tax | Business Effective Date and Business Effective End Date attributes to be added to Federal Luxury Tax entity | Pratik | 09/05 | Closed | [09/05] Pratik sent an email asking to add new attributes to Federal Luxury tax
Decision |  | Remove Attribute Federal Luxury Tax from Federal Luxury Tax custom object |  | Pratik | 09/09 | Closed | [09/05] Pratik sent an email asking to remove Federal Luxury tax as it will have only GST and PST